## Issues
Key | Type | Epic Key | Title | Body | Labels | Sprint | Story Points
E1 | Epic |  | Epic: Account & Family Management | **Goal:** Enable parents to create accounts, add children, and manage family profiles. **Created:** 2025-08-09 **Stories:** (auto-linked by script) | type: epic | Sprint 1
E2 | Epic |  | Epic: Chore Management | **Goal:** Allow parents to create, assign, edit, and track chores, including recurrence and photo proof. **Created:** 2025-08-09 **Stories:** (auto-linked by script) | type: epic | Sprint 2-4
E3 | Epic |  | Epic: Reward & Allowance Tracking | **Goal:** Motivate children with a points-based rewards system, redemption, and approvals. **Created:** 2025-08-09 **Stories:** (auto-linked by script) | type: epic | Sprint 4-5
E4 | Epic |  | Epic: Progress & Reporting | **Goal:** Dashboards and reports for chores, points, and trends; optional leaderboards. **Created:** 2025-08-09 **Stories:** (auto-linked by script) | type: epic | Sprint 5-7
E5 | Epic |  | Epic: Notifications & Reminders | **Goal:** Push notifications for assignments, due reminders, and approvals with user settings. **Created:** 2025-08-09 **Stories:** (auto-linked by script) | type: epic | Sprint 6-7
E6 | Epic |  | Epic: Cross-Cutting Quality | **Goal:** Security, roles & permissions, real-time sync, offline, accessibility & UX polish. **Created:** 2025-08-09 **Stories:** (auto-linked by script) | type: epic | Sprint 1-8
E7 | Epic |  | Epic: Platform & DevOps | **Goal:** CI/CD, environments, logging/metrics, config, and project automations to support delivery. **Created:** 2025-08-09 **Stories:** (auto-linked by script) | type: epic | Sprint 1-2
S1.1 | Story | E1 | Parent account creation & login (email/password) | **User Story:** Parent account creation & login (email/password) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Create parent account with email verification flow. - Login/logout with secure session handling and refresh. - Password reset via email token (expires in 15 min). - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 1 | 5
S1.2 | Story | E1 | Phone login (OTP) and device trust | **User Story:** Phone login (OTP) and device trust **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Request OTP via SMS; enter code to authenticate. - Option to trust device for 30 days; revoke in settings. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 1 | 5
S1.3 | Story | E1 | SSO (Sign in with Apple/Google) for parents | **User Story:** SSO (Sign in with Apple/Google) for parents **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Support Apple and Google sign-in on iOS/Android/Web. - Link/unlink SSO to existing email account. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 2 | 8
S1.4 | Story | E1 | Create/Manage family (add/remove child accounts) | **User Story:** Create/Manage family (add/remove child accounts) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Add child profile with name, avatar, birth year. - Deactivate/reactivate child without data loss. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 1 | 5
S1.5 | Story | E1 | Parent/Child roles & permissions | **User Story:** Parent/Child roles & permissions **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Parents can manage chores/rewards; children cannot alter assignments. - Unauthorized actions blocked and audited. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 2 | 3
S1.6 | Story | E1 | Profile settings (avatars, display names, time zone) | **User Story:** Profile settings (avatars, display names, time zone) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Upload/select avatar; sanitize/resize images. - Time zone stored per family for due-date rendering. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 2 | 3
S2.1 | Story | E2 | Create chore (title, description, due date, assignee[s]) | **User Story:** Create chore (title, description, due date, assignee[s]) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Create chores assigned to one or more children. - Due date picker respects family time zone. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 2 | 5
S2.2 | Story | E2 | Set chore value (points or monetary) | **User Story:** Set chore value (points or monetary) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Parent selects points or $ value; stored in chore schema. - Displayed consistently in child and parent views. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 2 | 3
S2.3 | Story | E2 | Edit/Delete chores with history | **User Story:** Edit/Delete chores with history **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Edit attributes; maintain change history (who, when, what). - Soft-delete with undo within 30 minutes. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 3 | 3
S2.4 | Story | E2 | Recurring chores (daily/weekly/monthly rules) | **User Story:** Recurring chores (daily/weekly/monthly rules) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Support RRULE-like schedules (e.g., Mon/Wed/Fri). - Auto-generate upcoming instances for 30 days. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 4 | 8
S2.5 | Story | E2 | Child marks chore complete (+optional photo proof) | **User Story:** Child marks chore complete (+optional photo proof) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Child can toggle completion; uploads optional photo evidence. - Uploads scanned for size/type; stored securely. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 3 | 5
S2.6 | Story | E2 | Parent review/approve chore completion | **User Story:** Parent review/approve chore completion **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Parent can approve/reject with comment. - Upon approval, points credited to child balance. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 3 | 5
S2.7 | Story | E2 | Bulk assign chores to multiple children | **User Story:** Bulk assign chores to multiple children **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Create one chore and fan-out per-assignee instances. - Prevent double crediting for shared chores. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 4 | 5
S3.1 | Story | E3 | Rewards catalog (items, experiences, cash/custom) | **User Story:** Rewards catalog (items, experiences, cash/custom) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Parents can add/edit rewards with images and descriptions. - Rewards can be marked as out-of-stock or inactive. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 4 | 5
S3.2 | Story | E3 | Set reward cost in points/currency | **User Story:** Set reward cost in points/currency **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Support per-reward cost; currency displayed based on locale. - Prevent negative balances on redemption. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 5 | 3
S3.3 | Story | E3 | Child redemption request flow | **User Story:** Child redemption request flow **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Child requests reward; confirmation shown with expected deduction. - Request enters 'Pending Approval' state. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 5 | 5
S3.4 | Story | E3 | Parent approval of redemption | **User Story:** Parent approval of redemption **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Parent approves/denies with comment; child notified. - On approval, points deducted; delivery instructions logged. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 5 | 3
S3.5 | Story | E3 | Allowance payouts (optional weekly) | **User Story:** Allowance payouts (optional weekly) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Configure weekly allowance per child with payday. - Auto-transfer to parent's ledger for payout tracking. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 5 | 5
S4.1 | Story | E4 | Parent dashboard: chores, approvals, points | **User Story:** Parent dashboard: chores, approvals, points **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Single view shows pending approvals and weekly progress. - Tiles/cards responsive on mobile and web. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 5 | 5
S4.2 | Story | E4 | Weekly & monthly email summaries | **User Story:** Weekly & monthly email summaries **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Parents receive summary; can opt-out per settings. - Includes top contributors and missed chores. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 6 | 3
S4.3 | Story | E4 | Leaderboard (optional) | **User Story:** Leaderboard (optional) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Toggle per family to enable/disable competition view. - Ties handled consistently; anonymize if desired. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 7 | 5
S4.4 | Story | E4 | Export data (CSV) for family history | **User Story:** Export data (CSV) for family history **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Parents can export chores and rewards history. - Download link secured and expires within 10 minutes. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 6 | 3
S5.1 | Story | E5 | Push notifications: new chores & due reminders | **User Story:** Push notifications: new chores & due reminders **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Notify child when new chore assigned; remind day-of and 1 hr before. - Quiet hours support; respects device-level settings. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 6 | 5
S5.2 | Story | E5 | Parent notifications: completions awaiting approval | **User Story:** Parent notifications: completions awaiting approval **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Notify parent when child marks complete. - Bundle notifications to avoid spam. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 7 | 3
S5.3 | Story | E5 | Notification settings per user | **User Story:** Notification settings per user **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Parents/children can toggle categories (assignments, approvals, promos). - Settings sync across devices. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 7 | 3
S6.1 | Story | E6 | Role-based access control (RBAC) enforcement | **User Story:** Role-based access control (RBAC) enforcement **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - All API routes guarded with role middleware. - Security tests simulate prohibited actions. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. - Authenticated endpoints require appropriate role (parent/child). - Idempotent retries safe; request/response schemas versioned. - Errors use consistent problem+json with machine-readable codes. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 8 | 5
S6.2 | Story | E6 | Real-time sync using websockets/subscriptions | **User Story:** Real-time sync using websockets/subscriptions **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Cross-device updates appear within 2 seconds. - Backoff/retry strategy on disconnect. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 8 | 8
S6.3 | Story | E6 | Offline support: mark complete & queue sync | **User Story:** Offline support: mark complete & queue sync **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Child can mark complete offline; queued and reconciled on reconnect. - Conflict resolution favors latest approval decision. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 8 | 5
S6.4 | Story | E6 | Accessibility & kid-friendly UI polish | **User Story:** Accessibility & kid-friendly UI polish **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Meets WCAG AA for core flows; large touch targets. - Colorblind-safe states; haptic feedback on mobile. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 8 | 5
S7.1 | Story | E7 | CI/CD pipeline (build, test, lint, deploy to dev) | **User Story:** CI/CD pipeline (build, test, lint, deploy to dev) **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - PRs run unit tests & linting; status required for merge. - Auto-deploy main to dev environment. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 1 | 5
S7.2 | Story | E7 | Project automation: fields (Sprint, Story Points) & iterations | **User Story:** Project automation: fields (Sprint, Story Points) & iterations **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Create 'Sprint' iteration field (8×14 days starting 2025-08-11). - Create 'Story Points' number field and expose in board view. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 1 | 3
S7.3 | Story | E7 | Health checks: missing points/sprint/epic linkage report | **User Story:** Health checks: missing points/sprint/epic linkage report **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Nightly job exports CSV and flags gaps. - Summary comment posted to project discussion. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 2 | 3
S7.4 | Story | E7 | Observability: structured logs & metrics | **User Story:** Observability: structured logs & metrics **Description:** Implement per BRD/Roadmap. Ensure parent-child roles, sync, and security. **Acceptance Criteria:** - Centralized logs (request id) with PII scrubbing. - Key metrics: DAU, chore completions, approval latency. - All inputs validated with inline, actionable errors. - Accessible: labeled controls, keyboard reachable, screen-reader friendly. - Unit tests cover core logic; e2e smoke test for happy path. - Audit log entry for create/update/delete actions where applicable. - Telemetry event(s) emitted for key user actions. - Degrades gracefully offline (where specified); sync on reconnect. **Definition of Done:** - Code reviewed and merged; tests passing in CI. - Story Points updated; added to Sprint iteration. - Screenshots or short loom/gif attached for UI changes. - Release notes entry prepared if user-facing. | type: story | Sprint 2 | 5